## Predes.
A CHECKLIST FOR PROJECT PLANNERS | [5 empty] | June 2013 edition
Pre-design Phase
info archived at
| done or NA | under way | to do | CPRE files | proj planner | server
Project summary: one page description
sponsor: write charge to user group
Find start up money, set up accounts
Collect info from previous studies, capital construction requests, etc.
Identify management group, start weekly check-ins (meet or phone)
Provide user group chair with this list, basic description of roles & responsibilities, etc.
Establish Technical Issues group information/scoping meeting with Facilities, Network Services, EHS, etc.
Check site:
- review of utilities map
- environmental hazards (Level 1 EA?), coordinate with EHS
- order site survey, or develop other planning base for this phase
- assemble geotechnical information from CPRE library
Initial scoping meeting with project sponsor
- identify “alligators”
neighboring users
neighborhood groups
City code, building code, fire code issues
- identify “go-to” person on user side for management & const. meetings
- map out process: procedure manual, this checklist. review/adjust as needed
- map out project schedule through final occupancy
- monitor legislative limitation issues
- introduce procurement/delivery choices, with FS make decision
Build pre-design project budget
- distribute to Facilities Services, project sponsor, VPFA?, review meeting,
- conduct or confirm cost/scope assumptions to guide programming process
(avoid “week before Christmas” syndrome)
- develop financial pro-formas, cash flow analyses, etc. as needed
Develop or commission project program
State Energy Efficient Design program (SEED)
- notify Facilities energy staff (Jeff Madsen)
- notify Office of Energy (Jeff Madsen)
- establish process and timeline for hiring energy analyst (planner + Jeff)
For CPC meeting 1:
- identify patterns and policies
- identify preferred site
- identify user group, name chair
Establish communication parameters:
- advance info __ days ahead of meetings (min. 1)
- brief notes or summary within one week of meetings, by whom?
Visit site with users, discuss site constraints and opportunities
Work with user group to identify broad goals, aspirations, and detailed concerns
With users, review patterns and create project-specific patterns
Write project description for hiring architects
Hire architects
- draft RFQ
- OUS conflict of interest forms for selection panel
- write/update contract template
- screen, rank qualification submittals
- invite firms for interview
- select preferred firm
- negotiate contract
- provide core documents: Campus Plan, Oregonized ADAAG, Construction Stds, etc.
Map out design process with architect: scope goals, tasks & mtgs through SD
Establish protocols for advance materials, meeting note documentation, etc.
Hire CM/GC
Sustainability scoping (can be earlier)
- establish participants and map process
- identify environmental issues & values, relevant UO and State policies, laws
- set goals and priorities
- discuss opportunities and strategies
- establish metrics and performance targets
- document in draft Owner’s Project Requirements (OPR)
- meeting notes, SD report- document in project intentions paper
Check in with Planning staff for project review
Historic designation check of existing site & buildings
Check in with City plan review staff, land use staff, if appropriate
Identify construction project manager, planner and PM develop work plan, review
Check with HR re need for lactation room
Conduct value-setting session among users, design team, contractor
Conduct quarterly financial review (funding, budget) or as end-of-phase activity

## Schematic
A CHECKLIST FOR PROJECT PLANNERS | [5 empty] | June 2013 edition
Schematic Design Phase
info archived at
| done or NA | under way | to do | CPRE files | proj planner | server
If not already achieved, check off
- predesign sustainability items, above
- SEED items, above
- sustainability items, above
- ongoing weekly management check-in (w/ architect, contractor)
Notify Oregon Arts Commission re % for art process
Update budget based on program understanding
Set up user group meeting schedule
Set up focus groups, departmental users, and other input methods, as needed
(quick tech group check-in before dd?)Conduct information session early in SD with other UO entities through Technical Issues group or individual discussions:
- Facilities maintenance zone
- Network Services/Telecom
- Facilities central plant
- Departmental or College support and/or technical staff
- EHS fire, stormwater, OSHA
- DPS
- CMET
- Registrar’s office
Conduct quarterly financial review (funding, budget) w/ planning, Facilities, VPFA
Value analysis: establish value points, areas needing more study- more for prog values than for systems
When concepts begin to jell, schedule
- informal CPC check-in review/discussion
- CPRE internal review (and invite FS?)
- mid-SD cost/scope review
Code check-in with City (with EHS) needs DD update
- fire and life safety narrative
- map fire access routes, hydrants add stormwater, SDCs?
- distribute notes within one week from CPRE
SEED meeting one or one/two: establish appropriate time in process with FS, ODOE –
- Set a review process and matrix for comments
- UO review process
Near end of SD
- obtain cost estimate(s), conduct value engineering/cost reduction session as needed
- review draft SD report with all stakeholders, Technical Issues group, etc.
- schedule CPC formal review meeting
With design team SD report checklist: format, patterns, level of detail
see note - Signoff of SD report by user group, including resolved cost estimate, budget, etc.
X Review CPRE documents protocol, SD files (paper and electronic) are complete
file of Unresolved items for DD
Review contractual requirements for SD phase
When all of above checked, authorize launch of Design Development phase

## Des. Dev.
A CHECKLIST FOR PROJECT PLANNERS | [5 empty] | June 2013 edition
Design Development Phase
info archived at
| done or NA | under way | to do | CPRE files | proj planner | server
DD kick-off for user group:
- review CPC comments/requirements and Campus Plan compliance
- finalize pattern discussion (if not earlier)
- establish DD schedule of critical dates (especially wall freeze, DD review, etc.)
Conduct DD Technical Issues kickoff meeting with Facilities, Network Svs., EHS, CNET, etc. (if not done de facto in SD reviews)
Propose exterior envelope systems
Freeze location of structural grid, lateral restraint system
Generate with users desired service points for power, data, loads for power
Amplify on SD code review in more detail. Identify all known needed AM&Ms
Review code compliance strategy with City staff
Conduct phase permit meeting with City if needed
Mid-DD cost estimate and budget update
Develop initial SDC spreadsheet, review assumptions with City staff
Agree on extent of systems documentation in DD with project mgr and design team
Conduct value discussion or update previous with users/contractor/design team
User review of initial concepts for interior finishes and materials, colors
Establish parameters for maintenance access tbuilding systems
Determine extent of preservation/removal of historic fabric
Finalize strategy re window repair/replacement (for renovation projects)
Mid-DD update Sustainability Plan, OPR, etc.
User sign-off on freezing walls, doors, openings tallow orderly progress by MEP, etc.
Forward floor plans tFacilities Services tdevelop room numbering
Draft Bicycle Management Program parking demand analysis
Map out maintenance access texterior envelope (roof, walls, windows)
Develop initial furniture and equipment layouts, spreadsheets, review with users
Develop demolition scope for existing facilities thand off thaz. material staff
With CMGC, develop initial construction staging/impacts plan
DD final review meetings
user group appproval
technical reviews
EHS
AV/CMET/media
Network Services
Catering/food service (if applicable)
FS Exterior team
FS Custodial and finishes (and FS Zone maintenance?)
FS Plumbing, Mechanical, Controls
FS Electrical
FS Utilities (power, chilled water, steam)
DPS & FS Lockshop for security
FS Lockshop doors/locks/access controls
DPS parking
support staff in administrative unit occupying building
technical
office
other
FS Elevators
Classroom committee reps
Exterior envelope review with FS zone
Collate all comments in comment tracking spreadsheet
Final DD update Sustainability Plan, OPR, etc.
Consider a SEED update session sthat final SEED decisions aren’t late surprises
Final DD cost estimate, reconciliation, and cost reduction as needed
Final DD budget update
DD budget review with project sponsor, VP, user group chair
Review CPRE documents protocol, DD files (paper and electronic) are complete
Code Alt. Means & Methods drafts, applications, approvals recorded
DD progress sets (e.g. 50%)
DD progress set cost estimate, reconciliation, and cost reduction docs
100% DD set: plans, outline specifications, cut sheets
DD cashflow forwarded to Bus. Affairs & Budget
Contractual requirements to complete DD phase
CPC reqs: check w/ CT or w/ file

## Const. Docs.
T | B | D