## Sheet1
University of Oregon Process for Design and Contruction of Major Capital Projects
Campus Planning & Real Estate v:8 August 2012
Phases, Activities and Check Points
|  |  |  | Before fund-raising > > > > > > > > |  |  | Before full funding > > > > > > |  |  | After full funding > > > > > > > > > > > > > > > > > > > > >
|  |  |  | Speculation | Formulation and prioritization | Approval to raise funds | Capital const. list, legislative authorization | Architectural Program | Conceptual design | User Group start-up |  | Pre-design, hire architects |  | Schematic design |  |  | Design develop't |  |  | Construction documents | Bid/ Award | Construction | Occupy/ Warranty
Check Points
Campus approvals
|  | Dean/Director |  |  | t |  | t | t |  |  | t |  | t |  | t |  |  |  |  | t | t
|  | User Group | [8 empty] | t |  | t |  | t |  |  | t
|  | Provost/VP Finance & Admin/VP Univ. Devel. |  |  |  |  | t
President
|  | VP Finance & Admin. (on behalf of President) | [10 empty] | t |  | t
|  | Campus Planning Committee | [8 empty] | t |  | t |  | t
| Off-campus approvals | [5 empty] | t
|  | OUS |  |  |  |  | t
Legislature
Critical variables
|  | Institutional mission |  |  | l |  | l | l
|  | Funding |  |  |  |  | l | [5 empty] | l
|  | Plan compliance |  |  |  |  | l | [7 empty] | l
|  | Cost, scope, schedule, impacts |  |  |  |  | l | [7 empty] | l |  |  | l |  | l | l | l
Participants
On-campus
|  | President or designee (e.g. VPFA) |  |  |  | t | t | [8 empty] | t |  |  |  |  | t
|  | Sr. VP, VPs |  |  |  | t | [9 empty] | t
|  | Deans/Directors/Project Sponsors |  |  | t |  | t | t | t |  | t |  | t |  | t |  |  |  |  | t | t
|  | Campus Planning & Real Estate project staff | [7 empty] | t |  |  | t | t | t | t
|  | User Group | [8 empty] | t |  | t |  | t |  |  | t | t
|  | Campus Planning Committee | [7 empty] | t |  |  |  | t | t | t
|  | Capital Projects dept, Campus Operations | [17 empty] | t | t | t | t
Facilities-related entitites
Operations/zone maintenance
Recycling
Public Safety
Central Power Station
Environmental Health & Safety
Energy
Locks and Doors
Emergency Management
Network services/Telecommunications
Campus Planning staff review
CMET
Business Affairs and Budget
Project/Unit financial staff
|  | General Counsel & contract review | [10 empty] | t | [7 empty] | t
Development
Disability Services/AAEO/Campus Planning (ADA)
Off-campus design consultants and builders
Conceptual Design firm (if used)
Architectural Programmer (if used)
|  | Architecture/Engineering/Landscape Arch. team | [18 empty] | t
|  | Construction Manager/General Contractor | [18 empty] | t
Off-campus regulators
|  | City of Eugene | [18 empty] | t | t | t
Oregon Department of Energy
|  | US Green Building Council | [20 empty] | t
LEGEND
| t | sign-off or check-in
responsibility
advisory involvement
[22 empty] | [add note re alt |  | l t q
procurement]