## Sheet1
Project Delivery Spreadsheet - [insert project title here] | [11 empty] | [insert date/version]
KEY
PL=Planning - [insert planner name], Project Planner |  | L=lead, P=participate, I=invite, D=distribution list
CC=Capital Construction - [insert PM name], Project Manager
user group | predesign |  | schematic des |  | design dev |  | const. doc |  | bidding |  | const adm |  | warranty
user group meeting facilitation, scheduling | PL-L | CC-D | PL-L | CC-I | PL-L | CC-P | PL-L | CC-P
lead management group meetings, provide notes | PL-L | CC-D | PL-L | CC-P | PL-L | CC-P | PL-L | CC-P
user meetings, provide visual notes, monitor archt's notes | PL-L | CC-D | PL-L | CC-I | PL-L | CC-P | PL-L | CC-P
collate & track user group comments | PL-L | CC-D | PL-L | CC-D | PL-L | CC-D | PL-L | CC-P
manage SD & DD sign-offs |  |  | PL-L | FS-P | PL-L | CC-P | PL-L | CC-P
communication with User Group Chair | PL-L |  | PL-L | CC-D | PL-L | CC-D | PL-L | CC-P | PL-D | CC-L | PL-D | CC-L | PL-D | CC-L
impacts, notification & coordination of neighbors (noise, etc.) |  |  | PL-L | CC-I | PL-L | CC-P | PL-P | CC-L | PL-P | CC-L | PL-I | CC-L | PL-I | CC-L
budget | predesign |  | schematic des |  | design dev |  | const. doc |  | bidding |  | const adm |  | warranty
build initial budget model
budget tracking - monthly
identify and track funding sources
cost consultant hire and cost estimating
initiate budget reviews by phase or quarter
quarterly project cash flow projections
design items | predesign |  | schematic des |  | design dev |  | const. doc |  | bidding |  | const adm |  | warranty
parking agreement(s)
bike parking analysis for permit
furniture design / selection
furniture procurement / installation
AV design / selection | [14 empty] | -
AV procurement / installation
signage design / selection | [14 empty] | -
signage procurement, installation
construction standards, exceptions
art design / selection
art installation
city reviews, AM&Ms/written agmnts
submit plans for permit
design team | predesign |  | schematic des |  | design dev |  | const. doc |  | bidding |  | const adm |  | warranty
hire architects
provide Standards to design team
monitor architect's contract
review additional service requests
process additional service requests
hire cost estimator, monitor contract
hire energy analyst, monitor contract
energy/SEED process & requirements
hire commissioning agent, monitor contract
attend/monitor architect's consultant meetings
consultations & submission to City
architect payment applications
11th month walkthrough prior to warranty end
on-site coordination | predesign |  | schematic des |  | design dev |  | const. doc |  | bidding |  | const adm |  | warranty
procure site survey
procure geotech report and ind. 3rd party (if req'd)
asbestos / haz-mat survey & report
procure environmental assessm't (if req'd)
design team and contractor on-site investigations
contractor activities | predesign |  | schematic des |  | design dev |  | const. doc |  | bidding |  | const adm |  | warranty
hire CM/GC
monitor CM/GC contract
project phasing determination & methods
value-setting sessions
value engineering sessions
constructability reviews between Arch/CMGC
CM/GC cost estimating
Pre-Construction Meeting(s)
OAC construction meetings
RFI/CCD review and processing
change order review & processing
contractor payment applications
11th month walkthrough prior to warranty end
UO review | predesign |  | schematic des |  | design dev |  | const. doc |  | bidding |  | const adm |  | warranty
coordinate CPC reviews/approval
50% and 100% document distribution & review
coordinate technical review meetings
collate and track UO technical comments
inform users, User Group chair re CA changes
manage Standards substitions
manage project history / documentation
schedule | predesign |  | schematic des |  | design dev |  | const. doc |  | bidding |  | const adm |  | warranty
manage schedule